## Strategies and measures
Strategies and measures
Table 2.1 - Strategies and measures progress
Required | Required | Required
Strategies and measures | Status | Status description
List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change.
Strategies and measures | Status | Status description
1.1 HSV has not previously collected all gender equality data required by the Workplace Gender Audit. This impacts the organisation’s ability to determine strategies and develop actions. a) Improve systems to collect gender equality data by updating HR systems to allow: intersectional data to be collected and employees to select their gender, including an option of ‘self-described’. | Complete | In June 2021 HSV commenced the collection of intersectional data for new employees, as per the gender equality audit. In addition, HSV's HR systems were updated to store intersectional data prior to the 2023 gender equality audit, meeting the timeline specified for this action item. Employee communications encouraging employees hired before June 2021 to provide their intersectional data for inclusion in the 2023 Gender Equality Audit was also implemented. These initiatives provide HSV insight into the intersectional gender equality and areas for improvement for our employees.
b) Review processes for collecting and reporting on data required for the Workplace Gender Audit. | Complete | HSV has improved processes for collecting information on recruitment and promotions, flexible work arrangements and learning and development activities. This was implemented within the timeline specified for this action item. This information provides HSV greater insight into gender equality outcomes in these areas.
1.2 Support employees in expressing their identity at work, including their gender. a) Continue to deliver Diversity and Inclusion initiatives for First Nations people, cultural diversity, accessibility, mental health, LGBTIQ+ status, and gender equality. | Ongoing | HSV continues to deliver on the six key focus areas of the HSV Diversity and Inclusion Plan. The HSV Diversity and Inclusion Plan outlines our strategy to foster and develop diversity and inclusion at HSV. Activities in the plan focus on raising awareness, promoting the tangible benefits of inclusion and supporting our workforce in valuing diversity and workplace respect.
b) Build trust with employees completing employee surveys including the People Matter Survey by reinforcing in all communications that: all responses are confidential; feedback is listened to; actions are developed and implemented collaboratively with employees. | Ongoing | HSV continues to communicate the confidentiality of feedback for all employee surveys. HSV's 2023 People Matter Survey response rate was 87%, up from 81% in 2022.
c) Introduce gender pronouns in email signature blocks – she/her, he/him, they/them: optional for employees; supported by training and communication. | Complete | Implemented in 2022 within the specified timeline. Gender pronouns were introduced to email signature blocks with the support of a presentation at a HSV Huddle (team meeting), toolbox meeting and a follow up Learning Lunch from an employee undertaking Post-Graduate studies in Sexology and Counselling. A 20 minute recording of the team meeting presentation and additional information has been included in the online induction program. HSV continue to promote gender pronoun inclusion by recognising International Pronouns Day and regular reminders to employees to update their pronouns in their email signature block.
d) Promote existing all gender toilets at HSV including Casselden Place and Derrimut Distribution Centre by: updating induction materials; communicating to employees. | Complete | All gender toilets were promoted through an Intranet article and have been noted in HSV's online induction program.
1.3 Continue to use up to date information on gender equality for decision making purposes. a) Report divisional gender composition metrics and trends to the Executive Leadership Team (ELT). | Ongoing | PCS continue to report gender composition metrics and gender pay gap trends to the ELT on a monthly basis as part of the people metrics reporting. This informs planning and decision making.
2.1 Support equal opportunity for all genders to participate on HSV's Board of Directors. a) Continue to facilitate Victorian Public Sector Board appointments. | Ongoing | HSV continue to facilitate Victorian Public Sector Board appointments.
3.1 Uphold the principles of equal pay for work of equal or comparable value. a) Embed pay equity principles in remuneration classification structure. | In progress | The role classification review encompassing a review of band level remuneration is currently under negotiation with the CPSU and will be included in the review and update of the HSV Enterprise Agreement. It will provide clear descriptors for role classification and remove overlapping remuneration bands.
b) Continue current remuneration practice to offer equal pay for roles of equal value. | Ongoing | HSV continue the practice to offer equal pay for roles of equal value through its recruitment processes.
c) Explore options for managers to complete extended unconscious bias training (covering recruitment, pay equity, leave and flexibility). | Ongoing | The timeframe for completing this action has changed to reflect an updated delivery plan. This is now an ongoing action. Rather than delivering a general unconscious basis course to people leaders, HSV are incorporating elements of unconscious bias into all learning and development programs. Most recently unconscious bias has been discussed with all employees in our Team building and fostering psychological safety program. It is also covered in our recruitment and selection module.
3.2 Analysis of gender pay equity. a) Continue to monitor and report on gender pay equity to the Executive Leadership Team. | Ongoing | PCS continue to report gender composition metrics and gender pay gap trends to the ELT on a monthly basis as part of the people metrics reporting. This informs planning and decision making.
4.1 Educating employees about sexual harassment and other inappropriate behaviours can reduce the prevalence of sexual harassment in the workplace. a) Continue all new employees participating in face-to-face Diversity and Workplace Respect training as part of their induction. | Ongoing | By the end of 2023, >90% of current employees will have completed Diversity and Workplace Respect training. For this training all new starters complete a 30 minute online training module followed by 2.5 hour in person Diversity and Workplace Respect training that covers: •Defining bullying, harassment, sexual harassment, and appropriate workplace behaviours and how it intersects with human rights and responsibilities. •Understanding the relevant legislation including understanding the legal risks to the organisation of bullying behaviours. •Identifying behaviours that are considered bullying, and those that are not. •Appreciating the impact bullying, harassment and other unlawful behaviours can have on an individual, including their wellbeing and performance. •Understanding the options available for someone being treated unfairly or subjected to inappropriate workplace behaviours, including the complaint resolution procedure. •Strategies to help someone being bullied. •Links with HSV’s Speak Up program.
b) Continue to refresh employees’ knowledge of the Diversity and Workplace Respect and Complaint Resolution policies and procedures through HSV’s compliance program. | Ongoing | HSV has updated the system used to deliver the compliance program to employees which has delayed the refresh of the diversity and workplace respect and complaint resolution procedure in 2023. It will be scheduled for 2024.
c) Develop online learning module on resolving complaints. | Void/cancelled | Due to changing priorities this action has been cancelled. This information is included in our Diversity and Workplace Respect and Complaint Resolution Procedure which is reinforced through online compliance training and Diversity and Workplace Respect training. The development of this online module may be revisited at a future date.
4.2.1 Continue current programs and initiatives to address negative behaviours including sexual harassment. a) Speak Up topics addressing negative behaviours including sexual harassment. | Ongoing | HSV has met this action to deliver one Speak Up topic addressing negative behaviours each year. Casual sexism and micro behaviours and affirmation topics were discussed by Speak Up groups in 2022, workplace bullying and aggression and putting our values into action topics were delivered in 2023.
b) Speak Up topic addressing casual sexism. | Complete | This action was completing within the timeline. 29 groups of employees discussed the Speak Up topic on casual sexism in March 2022. The topic asked employee groups to discuss: • When have I seen or experienced everyday sexism? • What can I say to speak up when I witness it? • What do I do if I get it wrong and cause offence? • How do I respond when I experience it myself? Feedback demonstrated this topic has improved employee understanding of casual sexism and sexual harassment.
4.2.2 Speak Up Contact Officers are a point of contact for an employee who believes they may be experiencing or witnessing inappropriate behaviours. Trained by the Victorian Human Rights and Equal Opportunity Commission, they provide information on the Diversity and Workplace Respect and Complaint Resolution procedures and options for resolving issues. a) Regularly promote our Speak Up Contact Officers to employees. | Ongoing | Speak Up Contact Officers meet every 8 weeks and during that meeting ideas for promoting the Contact Officer role are discussed. Speak Up Contact Officers have recently been promoted through Team meeting presentations and reminders, Intranet articles and Teams posts, posters and a new Intranet page 'Getting help - HSV support networks and programs' which lists all employees support role descriptions and employees in these roles, as well as other support resources.
b) Continue to build the skills of Speak Up Contact Officers through network meetings and refresher training. | Ongoing | The Speak Up Contact Officers attended refresher training with the Victorian Human Rights and Equal Opportunity Commission in February 2023. In addition, during the 8-weekly catch up meetings, learnings from contact officer meetings are shared (in a de-identified way). Contact officers provide feedback that the training, checklists and network meetings keep them ready to support an employees when needed.
c) Maintain a cross functional group of employees as Speak Up Contact Officers. | Ongoing | HSV has Speak Up Contact Officers in all Divisions across HSV and advertises vacancies as required. There are currently 8 Speak Up Contact Officers across HSV.
4.2.3 a) Regularly promote the Employee Assistance Program (EAP) at team meetings. | Ongoing | The EAP is regularly promoted at team meetings though presentations and reminders, Intranet articles and Teams posts and a new Intranet page 'Getting help - HSV support networks and programs' which has contact details of the EAP, employee support networks and other support resources. Utilisation rates for EAP are strong demonstrating employees are aware of this service.
4.2.4 Comprehensive Diversity and Workplace Respect and Complaint Resolution policies and procedures. a) Continue to refresh employees’ knowledge of Diversity and Workplace Respect and Complaint Resolution policies and procedures through HSV’s compliance program. | Ongoing | HSV has updated the system used to deliver the compliance program to employees which has delayed the refresh of the Diversity and Workplace Respect and Complaint Resolution procedure program in 2023. It is scheduled for 2024.
4.2.5 A comprehensive health and wellbeing program is a pillar of HSV’s BeSafe Safety Strategy. This covers psychosocial wellbeing, recognition, employee assistance program and HSV’s health and wellbeing committee (HAWC). a) HAWC continue to promote and celebrate: i. R U OK? Day, promoting meaningful connections and support of others in suicide prevention. ii. Harmony Day, celebrating Australian multiculturalism, and the successful integration of migrants into our community. iii. International Women’s Day, a global day celebrating the social, economic, cultural and political achievements of women. iv. International Day Against Homophobia, Biphobia, Interphobia and Transphobia, championing inclusion and building a better world for the LGBTIQ+ community. v. Men’s Health Week, promoting awareness of preventable health problems and encourage early detection and treatment of disease among men and boys. vi. National Aborigines and Islanders Day Observance Committee (NAIDOC) week, celebrating the history, culture and achievements of Aboriginal and Torres Strait Islander peoples. vii. World Mental Health Day, raising awareness of mental health issues around the world. viii. Movember, men’s health promotion and fundraising. ix. ix. International Day of People with Disability, increasing public awareness, understanding and acceptance of people with disability and celebrating their achievements and contributions. x. Skin screening xi. Flu vaccinations xii. Celebrations of achievements | Ongoing | These events have been delivered over the last 2 years. HSV employees have good engagement with HAWC events and promotions.
b) Continue formal and informal employee recognition programs | Ongoing | HSV's recognition practices continue. HSV has defined its employee value proposition in 2023 and a number improvement initiatives have been identified for completion in FY24, including a refresh of the employee recognition program. The refresh of the recognition program will improve visibility of the program and increase engagement with recognition practices at HSV.
4.3 Building employee trust and confidence to raise complaints will support them being addressed and resolved. a) Managers hold one-on-one meetings regularly with employees to ‘check in’ on wellbeing, understand challenges and barriers and support employees in addressing them. | Ongoing | It is an expectation that people leaders will meet 1:1 with employees at least monthly. This message is regularly reinforced through PCS Business Partners.
b) At team meetings, continue to regularly encourage reporting of inappropriate behaviours. | Ongoing | This message is regularly communicated to HSV employees. Reporting of inappropriate behaviours is reinforced through communication of the People Matter Survey results, regular temperature check updates, reminders about Speak Up Contact Officers and Speak Up topic announcements.
c) Continue to regularly promote Speak Up Contact Officers through the intranet, newsletters, team meetings and direct promotion by Speak Up Contact Officers. | Ongoing | Speak Up Contact Officers are regularly promoted through a variety of channels and Speak Up Contact Officers are receiving contacts from employees demonstrating employees are aware of their role.
4.4 Incident reporting provides another avenue for employees to report sexual harassment. A) Introduce incident reporting for inappropriate behaviours including sexual harassment. | Not started | HSV are exploring options for health and safety reporting with functionality to report inappropriate behaviour. This was planned for completion in 2022 however competing priorities has meant this project was delayed and is now expected to be completed in FY24.
4.5 Providing avenues for anonymous reporting of sexual harassment can allow HSV to monitor levels of inappropriate behaviour and target communications to encourage reporting and resolution. a) Continue to participate in the annual People Matter Survey and quarterly temperature check surveys, target communications and collaboratively develop and implement action plans as required. | Ongoing | HSV continues to participate in the annual People Matter Survey. Each year a detailed analysis of results is undertaken and targeted action plans are developed. Reports of inappropriate behaviour and improvements against actions plans are also monitored through a further temperature check survey in the same year.
5.1 Enhancing recruitment practices to promote gender equality principles will broaden the candidate pool of new HSV employees. a) Ensure interview panels are gender balanced. | Ongoing | Interview panels are gender balanced, where possible.
b) Request gender balanced shortlist from recruitment agencies (where possible). | Ongoing | Diverse shortlists are requested from recruitment agencies.
c) Promote awareness of language that contains gender bias to ensure position descriptions are attractive to all potential candidates. | Ongoing | The talent acquisition team work with recruiting managers to update position descriptions with gender neutral language.
d) Review the recruitment procedure for practices that may result in bias or discrimination and to ensure accessibility is maximised throughout the recruitment experience. | Not started | The review of the recruitment procedure is in progress.
5.2 Build capability of employees participating in recruitment activity. a) All recruitment panel members will complete the eLearning recruitment and selection training module, including the section on unconscious bias. | Ongoing | All recruitment panel members are assigned the eLearning recruitment and selection training module to support their participation in interviews. In addition, workshops to upskill recruitment panel members are planned for 2024.
5.3 Support employees to meet career aspirations. a) Continue to have regular career and development conversations and offer accessible learning and development opportunities to all employees in line with the 70:20:10 learning model. | Ongoing | Employees are encouraged to set an annual development plan during goal setting and review their progress at least every 6 months. PCS regularly provide guidance to people leaders on having career conversations and prompts to hold career conversations are included in the 1:1 meeting template. HSV offer employees access to 20,000+ courses through LinkedIn Learning and has an annual learning and development calendar focused on leadership, safety and diversity training. HSV also regularly communicate the principles of the 70:20:10 learning model to employees.
b) Monitor employee feedback on learning and development activities. | Ongoing | HSV offers employees the opportunity to provide feedback and make suggestions on all learning and development opportunities.
c) Recruiting managers provide constructive feedback and relevant actions to unsuccessful internal candidates. | Ongoing | It is an expectation that internal candidates who have applied for HSV positions and been unsuccessful will receive verbal feedback from the interview panel. This is supported by our Talent Acquisition team.
d) Communicate how the principles of merit and equity are upheld for all internal recruitment activities. | Ongoing | The recruitment and selection procedure outline how HSV maintains merit and equity throughout the recruitment process. The talent acquisition team continue to communicate and answer queries about merit and equity in internal recrutiment and this is an area that will be addressed through HSV's 2023 People Matter Survey Action Plan.
6.1 Flexible Work Arrangements can support Employees in achieving a balance between work, personal and family responsibilities. HSV is genuinely committed to offering employees flexible work arrangements that meet the individual’s need for flexibility as well as HSV’s business and legislative requirements. a) Continue to coach managers to manage and accommodate flexible work arrangement requests. | Ongoing | HSV's people leaders are supported by PCS Business Partners to respond to, and accommodate where possible, requests for flexible work arrangements.
b) Continue to build manager capability by exploring options to utilise the resources from external organisations, e.g. eLearning options and sharing resources through the health sector community of practice. | Ongoing | PCS maintain relationships with health sector and Victorian Public Service colleagues and share information regarding learning opportunities by attending the monthly Defined Entity Gender Equality VPS working group meetings.
c) Continue to monitor employee feedback in surveys, including the People Matter Survey, and develop action plans as appropriate to support employees in accessing flexible working arrangements. | Ongoing | Each year a detailed analysis of People Matter Survey results is undertaken at the organisational and divisional level and targeted action plans are developed. In 2023, 80% of employees responded positively to questions about working flexibly in the People Matter Survey.
6.2 HSV is committed to providing a safe and supportive work environment and to supporting Employees who experience family violence. a) Continue to provide family violence training for all employees, including specific manager training. | Ongoing | HSV offer family violence awareness training through our Employee Assistance Program provider. This program is facilitated by a psychologist trained to provide support to people experiencing family violence, those supporting others experiencing family violence and perpetrators. This training brings awareness to a significant issue in our community and focuses on how we can support our colleagues, friends and family by starting a conversation and connecting people to support. There is an additional 30 minute session for people leaders to focus on understand their responsibilities for supporting their team. In addition HSV offers employees to have a 1:1 meeting with the psychologist following the training.
7.1 Aspire to achieve gender equality across HSV. a) Actions as per recruitment indicator relating to gender balanced interview panels, gender balanced shortlists, language and procedure review. | Ongoing | See responses against gender equality indicator 5 above.
b) Explore options for building employees’ understanding of the impact of gender inequality in the workplace. | Not started | 2024 action
c) Engage with Women Victoria to explore how HSV employees can get involved in future women’s leadership programs. | Ongoing | PCS are continuing to monitor offerings for women's leadership programs with Women Victoria. HSV have commenced their leadership program in 2023 with a 1 day program for all people leaders on safety leadership and a 0.5 day program on fostering psychological safety. Other priorities for FY23 include mental health awareness and giving and receiving feedback as well as defining our leadership capability framework.
d) Explore options for increasing the number of women in the Distribution operations team, e.g. internships. | Ongoing | HSV's gender composition for the Distribution operations team has shifted since the initial gender equality audit. In 2021, 100% of employees were men. By June 2023 women employees represent 16% of the Distribution operations team are women.
7.2 HSV can contribute to breaking down stereotypes and celebrate our diversity. a) Promote employee intersectionality through the promotion of employee diversity, men and women working in non-traditional roles, flexible working etc. | Ongoing | HSV regularly spotlights employees through intranet articles, HSV Huddle presentations. Diversity and intersection information is provided as relevant.
b) Publicise key gender statistics and metrics via a number of platforms, e.g. website, annual report etc. | Ongoing | HSV includes gender statistics in the annual report.
c) Encourage participation in gender equality forums and events. | Ongoing | HSV participate in gender equality forums such as the Defined Entity Gender Equality VPS group and promote events such as International Women's Day, Men's Health Week, International Pronouns Day.

## Indicators
Workplace Gender Equality Indicators
Table 3 - Workplace gender equality indicators progress
Required | Required | Required
Indicator | Confirm if progress made | Progress description
This column contains the seven workplace gender equality indicators. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator.
Indicator | Confirm if progress made | Progress description
Gender composition of all levels of the workforce | Yes | HSV's gender composition balance has improved over the last 2 years. Gender equality audit results: women 42% 2021 to 45% 2023 men 58% 2021 to 54% 2023 self described gender 0% in 2021 (no data) to 1% in 2023
Gender composition of governing bodies | Yes | In the 2021 Gender equality audit, HSV's Board had a 50:50 gender balance. In 2023 the balance was 63% women to 38% men. Although there is not currently a gender balance on the HSV board, a higher representation of women improves the gender balance of boards across the VPS.
Equal remuneration for work of equal or comparable value across all levels of the workforce, irrespective of gender | No | In the 2021 gender equality audit, HSV's mean total remuneration gender pay gap was 4.7% in favour of women. At 30 June 2023, the gender pay gap was 5.2% in favour of men. Note, self described gender data not included to protect anonymity. In the 2023 gender audit, the largest gender pay gap in favour of men is two levels below the CEO (7.5% in favour of men). The gender pay gap is driven by a higher percentage of men in the highest pay groups compared to women. Pay gap % changes on a monthly basis due to the relatively small population. Numbers remain better than the national average and this remains a constant area of focus for HSV.
Sexual harassment in the workplace | No | In the 2023 gender equality audit, HSV recorded one formal sexual harassment complaint compared to zero in 2021. In the 2023 employee experience data, 2% of respondents reported expriencing sexual harassment (no change since 2021). Our employee experience data from 2023 confirms 72% of employees agree HSV takes steps to eliminate bullying, harassment and discrimination, down from 77% in 2021. Although HSV has not made an improvement by reducing reported sexual harassment at HSV, the results are below public sector (4%) and comparator (5%) averages and HSV's has a comprehensive program of actions to minimise sexual harrassment complaints, as outlined in the strategies and measures progress report.
Recruitment and promotion practices in the workplace | Yes | The gender equality audit results demonstrate the balance in gender equality in HSV's recruitment and promotion practices has improved over the last two years: People recruited - 2% more women have been recruited in the 2023 audit (52%) compared to 2021 (50%). Permanent promotions - the 2023 audit shows the balance of permanent promotions has improved with 46% of permanent promotions for women, compared to 100% promotions for men in 2021. Higher duties - the 2023 audit confirmed 44% of women were awarded higher duties, an increase of 11% since 2021 (33%). Internal secondments - the 2023 gender equality audit confirmed 67% of women were awarded internal secondments, representing a better balance of appointments from 100% of internal secondments being awarded to women in 2021. Career development - in 2023 participation in career development training was balanced at 50% men and 50% women, compared to 64% for women in 2021. The number of learning development opportunities for all employees in FY2022 increased significantly for all genders. Exits - 40% of exits in the 2023 gender equality audit were women compared to 64% in 2021. 2023 employee experience data says 61% of employees believe the recruitment processes are fair at HSV and 36% believe promotion proceses are fair. There are also a significant number of employees who don't know or neither agree nor disagree (20% and 39% respectively). This will be an area that is addressed as part of People Matter Survey action planning.
Availability and utilisation of terms, conditions and practices relating to: - family violence leave; and - flexible working arrangements; and - working arrangements supporting employees with family or caring responsibilities | Yes | HSV has made some progress against these indicators since the 2021 gender equality audit: Family violence leave - three employees utilised family violence leave in FY23 (an increase from zero in FY21). In 2023 employee experience data confirms 78% of respondents believe HSV would support them if they needed to take family violence leave. All employees at HSV are invited to attend family violence awareness training. Flexible work - 78% of respondents to the People Matter Survey utilise flexible work arrangements, 32% report they do not utilise flexible working arrangements. 5% of HSV respondents reported their flexible working are a barrier to success (below the public sector average of 7%). In addition, 84% of respondents reported their managers supports working flexibly (compared to 82% public sector average), only 5% of HSV respondents to the 2023 People Matter Survey disagree that their manager supports working flexibly. Since COVID many HSV employees at the Casselden site enjoy hybrid work, working both from the office and from home (if possible). Carers leave - continues to be balanced with 24 women and 22 men taking carers leave in 2023.
Gendered segregation within the workplace | Yes | Occupational segregation - areas identified for improvement in the 2021 audit have improved in 2023 including: Managers - 41% women in 2023, stable from 2021 Professionals - 52% women in 2023, up 3% from 2021 Machinery operators and drivers (warehouse and driver team) - 16% women in 2023, up from 0% women in 2021. This demonstrates an improvement in gendered segregation since 2021.

## Examples (hidden)
1 Gender impact assessments
| Title | Subject | Description | Status |  |  | Confirm if actions taken |  |  |  | Describe actions taken |  | Confirm intersectionality considered |  | Explain intersectional lens applied
| What is the title of the policy, program or service that was the subject of the GIA? Please use one row for each GIA completed. When reporting on multiple actions taken, include this information in the relevant single cell. | Was the subject of the GIA a policy, program or service? For definitions of policies, programs and services, please refer to the guidance materials at Appendix A: Glossary of terms. Use the drop-down menu in the cell to select your answer. | Provide a description of the policy, program or service subject to the GIA. | Was the policy, program or service new, or up for review? Use the drop-down menu in the cell to select your answer. |  |  | Were actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality as a result of the GIA? Use the drop-down menu in the cell to indicate whether or not actions were taken as a result of the GIA. |  |  |  | Describe the actions taken to develop or vary the policy, program or service to meet the needs of people of different genders, address gender inequality and promote gender equality. When reporting on multiple actions taken, include this information in one cell. You can press alt+enter to include new lines. |  | Was it considered that gender inequality may be compounded by disadvantage or discrimination that people may experience on the basis of intersectionality? Use the drop-down menu in the cell to select your answer. |  | Explain how an intersectional lens was applied while completing the GIA. If this was not done, explain why this was not practicable.
| Example: Sports ground use and permits policy | Policy | This policy guides the hire and use of all Council's sportsgrounds and facilities by sports clubs and the public. The policy outlines eligibility criteria for hire and use, selection and booking process, fees, payment options, cancellation options and expectations of use. | For review |  |  | Yes |  |  |  | Amended the policy to include a commitment to allocate 30% of the total sportsground hiring capacity to new and recently established sports teams comprising of women and gender diverse people. Amended the policy to include a commitment to support local clubs to conduct respect and responsibility training to promote gender equality. Amended the policy to include a commitment to provide dedicated womens and all-gender secured changerooms and facilities for all womens and gender-diverse teams who hire Council sportsgrounds. |  | Yes |  | Council conducted research and participated in consultation to ensure the GIA considered intersectionality. It was identified that language and shared changeroom facilities are percieved as major access barriers for culturally and linguistically diverse (CALD) women. Council has addressed these concerns in amending the policy, committing to implementing private changeroom areas and increased signage in a variety of languages.
2.1 Strategies and measures
| Strategies and measures | Status | Status description | Evaluation of success | [6 empty] | Timeline | Responsible | Relevant indicator(s)
[13 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7
| List your organisation’s strategies and measures. Include one strategy or measure per row. These are the planned actions that you have outlined in your GEAP to promote gender equality in your workplace. | Assign each strategy or measure a status from the following list: • ‘Complete’ indicates that all planned activities related to this strategy or measure have been finalised. • ‘In progress’ indicates that the activities under this strategy or measure are progressing but not yet complete. • ‘Ongoing’ indicates that the activities under this strategy or measure do not have an end-date and will be addressed on a continual basis. • ‘Not started’ indicates that the planned activities related to this strategy or measure have not yet commenced, including those that are intended to commence in future years. This should include strategies or measures that have been delayed. • ‘Void’ indicates that this strategy or measure appeared in your defined entity’s GEAP, but has since been cancelled. | Describe your progress in implementing each strategy or measure in your GEAP. In particular, you need to explain: • Why you have selected that status from the drop-down menu; and • Whether the status indicates any delay or change from what was planned in your GEAP and if so, the reason for this change. | Evaluating the success of each of your strategies or measures may include: • tracking against pre-identified success markers. These markers may have been specified in your GEAP. • other evaluation markers that may not have been specified in your GEAP, such as participation levels, outcomes, or changes resulting from the strategy or measure, • other ways the strategy or measure has contributed to promoting gender equality in your defined entity. | [6 empty] | If your GEAP included a timeline for action or implementation for your strategies and measures, include this timeline below. If you did not include a timeline in your GEAP, we highly recommend you do so in this progress report by including a timeline below. | Include the role or team responsible for implementing of each strategy or measure. | Identify one or more indicators for each strategy or measure that the action was designed to address. See the Indicators key to the right of this table for a description of each workplace gender equality indicator.
| Example: Address gaps identified in collecting intersectional data as part of employee and payroll systems | Complete | This strategy was implemented in March 2023. A payroll systems firm was engaged to upgrade our systems to support the collection of intersectional data in relation to sexual orientation, race, Aboriginality, religion, ethnicity, disability and gender identity. We have now begun collecting intersectional data and addressing the gaps identified in our 2021 audit. | Although originally anticipated for implementation in 2022, delays meant this strategy was implemented in March 2023. Intersectional data is being collected as part of new recruitments and promotions, and voluntary updates by existing staff. New intersectional data as part of our 2023 progress audit and future GEAPs will enable us to better understand intersectional gender equality in our organisation and areas for improvement. | [6 empty] | 2022 | People and Culture Corporate Support | X | X | X |  | X | X | X
3 Workplace Gender Equality Indicators
| Indicator | Confirm if progress made | Progress description | Factors | [6 empty] | Factors discussion
|  |  |  | a | b | c | d | e | f | g
| This column contains the seven workplace gender equality indicators. Complete the 'required' fields, and you are encouraged to complete the 'recommended' columns, to the right of each indicator. | Indicate whether your organisation has made progress in relation to the workplace gender equality indicators. Use the drop-down menu in the cell to select 'yes' or 'no.' | Demonstrate your progress in relation to each workplace gender equality indicator. In this column, please explain why you believe changes in your data do or do not represent progress against each indicator. Refer explicitly to quantitative changes in the data between your previous workplace gender audit and your progress audit. If you wish, you may also make reference to any strategy or measure from your GEAP that supported, or was designed to support, progress against that indicator. | Indicate below whether or not one of these factors has affected your organisation's progress against each indicator. You are encouraged to reference these factors in your discussion in column L. See the Factors key to the right of this table for a description of each factor. | [6 empty] | If you have selected 'yes' to any of the factors in the recommended columns to the left, you are encouraged to complete this column. This column allows you to discuss each factor that has affected your organisation's progress in relation to any of the workplace gender equality indicators.
| Example 1: Recruitment and promotion practices in the workplace | Yes | Recruitment In our 2021 audit, women represented only 35% of new recruits in the year to 30 June 2021. In our 2023 progress audit, this rose 6% to 41%. In 2021, of the women we recruited, 17% were employed on a full-time permanent basis, 14% on a part-time permanent basis and 69% on fixed-term contracts. In 2023, 22% of women recruited were employed on a full-time permanent basis, 20% on a part-time permanent basis and 58% on fixed-term contracts. We were not able to collect non-binary or gender diverse data in 2021. Our employee and payroll systems have since been updated to collect improved gender-diverse data. This has been achieved through the implementation of strategy 5.2 under our 2021 Gender Equality Action Plan (GEAP): ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. As such, in 2023, our data showed that 2% of new recruits identified as non-binary or gender diverse. Our organisation argues that these figures, in conjunction with successful implementation of relevant GEAP strategies, contribute to progress against Indicator 5. Not only have we been able to notably increase our recruitment of women and gender diverse employees, but we have also been able to offer these new recruits more attractive contract conditions. Stable contracts will also support us to retain employees of all genders and move towards a more gender-balanced workforce in the future. Promotions Our 2021 audit showed that 25% of promotions in the 12 months to 30 June 2021 were awarded to women. These promotions occurred in the lower and middle levels of the organisation only, and not within the executive leadership team. Our 2023 progress audit showed that 30% of all promotions were awarded to women, an increase of 5%. Of these, 10% occurred in the higher levels of the organisation and were ongoing permanent roles. Our organisation historically has a very stable executive leadership team where roles tend to be longer-term contracts or ongoing positions, with few exits. We are pleased to see promotion at the higher level of our organisation into ongoing positions for women. In 2021, we were not able to collect promotion data for non-binary or gender-diverse employees. In 2023, our updated systems allowed us to collect this data. However, there were no promotions awarded to this staff cohort. We believe that a significant aspect of our success in increasing the proportion of promotions awarded to women has been our focus on improving secondment and higher duties opportunities for women and gender-diverse employees. The proportion of secondments awarded to women increased by 5% and the proportion of higher duties by 6% between our 2021 workplace gender audit and our 2023 progress audit. Data on higher duties opportunities for gender diverse and non-binary employees was not collected in 2021, therefore there is no measured change in the data. We consider these improvements, while small, to demonstrate measurable progress against the workplace gender equality indicator ‘recruitment and promotion practices in the workplace’. We also believe the uptick in career development opportunities for women and resulting increase in women’s share of promotions demonstrates that our strategic approach is effective. We hope to see similar improvements for gender diverse employees reflected in our 2025 data. | No | Yes | No | No | No | No | Yes | As a largely male-dominated industry we recognise we have started from a lower baseline for this indicator and there is further to go. Despite this, we have made genuine efforts to attract and recruit a more gender diverse workforce by implementing the strategies identified in our GEAP, in particular: strategy 5.2 ‘Embed inclusive practices into our HR electronic systems. For example, offering a range of gender selection options’. We note that we are two years into the four-year GEAP implementation period, and as such have not fully implemented all GEAP strategies. The majority of our strategies against this indicator remain in early implementation stage. We believe our genuine efforts to implement strategies against this indicator and measurable progress arising from the data, demonstrate progress against indicator 5.
| Example 2: Sexual harassment in the workplace | No | Our 2021 Employee Experience Survey data showed that 7% of women and 4% of men who responded to the survey had experienced sexual harassment in the workplace, and of those 5% of women and 6% of men made a formal complaint. In 2023, our Employee Experience Survey data showed that 9% of women and 6% of men who responded to the survey reported having experienced sexual harassment in the workplace, an increase of 2% from 2021 for both cohorts. Of those, 9% of women and 10% of men indicated that they had made a formal complaint. Our 2023 Employee Experience Survey also indicated that women with disability were overrepresented among those who reported experiencing sexual harassment. We have initiated a review process to consider how we might address this between now and the 2025 reporting cycle. No respondents in our 2021 Employee Experience Survey identified as gender diverse. We also didn’t record any formal sexual harassment complaints in our 2021 workforce reporting data from employees of self-described gender. In our 2023 employee experience survey, 2% of respondents identified as non-binary or gender diverse. Of this cohort, 10% indicated experience of sexual harassment, with 50% of this group indicating that they had made a formal complaint. We note that these figures represent an increase in anonymous self-reporting of sexual harassment. This is concerning, as anonymous reporting tends to be more accurate than formal incident reporting processes. In analysing our 2021 and 2023 audit data, we found that our workforce reporting shows minimal change in terms of outcomes for formal complaints of sexual harassment. In 2021, our audit data showed that no outcome was reached for 70% of matters where the complainant was a woman, and 50% of matters where the complainant was a man. In 2023, our progress audit showed that of the incidents of sexual harassment reported by women, no outcome was reached for 65% of matters. This figure was 40% for men. We did not collect data on gender diverse and non-binary employees in 2021, nor their experience of sexual harassment. Our 2023 progress audit showed that of the incidents of sexual harassment reported by gender diverse and non-binary employees, no outcome was reached for 67% of matters. The enduring high levels of formal complaints with no outcome across our 2021 and 2023 audit data suggests that we have work to do in effectively and efficiently resolving sexual harassment complaints. The lack of outcomes for incidents of this type may contribute to our lack of progress in reducing sexual harassment. As a result of this analysis, we are reviewing our GEAP strategies and measures to consider how we might better respond to, and therefore hopefully reduce, sexual harassment in our organisation. We consider that the anonymous nature of the Employee Experience Survey data provides an accurate representation of sexual harassment. The increased sexual harassment reported via the Employee Experience Survey data indicates ‘no progress’ was made by our organisation against this indicator. | No | No | No | Yes | Yes | No | No | (e) Competing priorities and operational obligations Our organisation is a metro health service. During the recent covid-19 pandemic, Victoria’s public health system experienced unprecedented demand. In particular, rates of access to ICU and ventilation increased dramatically. As such, our organisation prioritised its public-facing service delivery. We directed the majority of our stretched resources externally to enable high-quality public health care. Demand outstripped supply, and already-stretched resources were directed to keeping ICU and general wards staffed. As a result, we were not able to deliver comprehensive in-person bespoke staff training in relation to sexual harassment, so instead delivered a low-cost e-learning module. We also lacked the resources to comprehensively review our internal sexual harassment processes. (d) Resources As described cell D9, our resources were significantly stretched due to an increase in demand for ICU services during the covid-19 pandemic. Competing priorities reduced the resources available for internal-facing programs, such as comprehensive sexual harassment training delivery and process review. For this reason, we focussed on low-cost strategies and measures in our GEAP, including delivering a sexual harassment e-learning module, circulating internal communications campaigns and encouraging staff to undertake the Employee Experience Survey. Our communications campaign focussed on drawing attention to existing sexual harassment policies including how the organisation will respond.

## (Hidden) REF (hidden)
Policy | New | Yes | Select one | Yes
Program | For Review | No | Complete | No action taken
Service |  |  | In progress
Ongoing
Not started
Void/cancelled